## Target
Issue Key | Filter | Summary | Platform | IP | Status | Due Date | Resolution
DS-1 | DS_issues | Baud Rate Test | JTAMP | UART | Fail | 2025-06-20 | Done
DS-2 | DS_issues | Parity Check Test | JTAMP | UART | Pass | 2025-06-06 | Done
DS-5 | DS_issues | Clock synchronisation Test | JTAES | SPI | Pass | 2025-06-23 | Done
DS-14 | DS_issues | Bus Arbitration Test | JTAES | I3C | Pass | 2025-06-07 | Done
DS-25 | DS_issues | Lane speed Test | JTAMP | PCIe | To Do | 2025-06-04 | Unresolved
DS-28 | DS_issues | Link stability analysis | JTAEN | PCIe | In Progress | 2025-06-13 | Unresolved
DS-33 | DS_issues | Signal Synchronization Test | JTAMP | LIN | To Do | 2025-06-07 | Unresolved
DS-34 | DS_issues | Frame error Analysis | JTAMP | LIN | Pass | 2025-06-07 | Done
DS-38 | DS_issues | Debug Interface Check | JTAES | JTAG | Fail | 2025-06-12 | Done
DS-39 | DS_issues | Signal Timing Analysis | JTAES | JTAG | Fail | 2025-06-21 | Done
DS-3 | DS_issues | Signal Integrity Test | JTAEN | UART | Fail | 2025-06-04 | Done
DS-4 | DS_issues | Loopback Test | JTAEN | UART | Fail | 2025-07-18 | Done
DS-9 | DS_issues | Address Conflict detection | JTAMP | I2C | Pass | 2025-06-01 | Done
DS-11 | DS_issues | Pull-up register Validation | JTAEN | I2C | Pass | 2025-06-25 | Done
DS-12 | DS_issues | Clock Streching Test | JTAEN | I2C | Fail | 2025-05-30 | Done
DS-13 | DS_issues | Address Conflict detection | JTAES | I3C | Fail | 2025-05-31 | Done
DS-17 | DS_issues | Error Frame Analysis | JTAMP | CAN | Pass | 2025-06-06 | Done
DS-20 | DS_issues | Node communication Verification | JTAEN | CAN | Pass | 2025-05-31 | Done
DS-21 | DS_issues | End point communication | JTAES | USB | Pass | 2025-06-06 | Done
DS-22 | DS_issues | Data Transfer Test Communication | JTAES | USB | Pass | 2025-06-07 | Done
DS-23 | DS_issues | Power consumption Analysis | SVB | USB | To Do | 2025-05-31 | Unresolved
DS-24 | DS_issues | Hot Plug Detection | SVB | USB | Pass | 2025-06-06 | Done
DS-29 | DS_issues | Packet Intergrity Analysis | JTAES | Ethernet | Pass | 2025-06-06 | Done
DS-35 | DS_issues | Bus Voltage Measurement | JTAEN | LIN | To Do | 2025-06-06 | Unresolved
DS-36 | DS_issues | Slave Response Time check | JTAEN | LIN | Fail | 2025-05-30 | Done
DS-37 | DS_issues | Boundary Scan Test | JTAES | Ethernet | Fail | 2025-06-05 | Done
DS-6 | DS_issues | Data Transfer Test | JTAES | SPI | To Do | 2025-06-19 | Unresolved
DS-7 | DS_issues | Salve select Validation | SVB | SPI | Fail | 2025-06-05 | Done
DS-8 | DS_issues | Signal Noise Analaysis | SVB | SPI | In Progress | 2025-06-07 | Unresolved
DS-10 | DS_issues | Bus Speed Analysis | JTAMP | I2C | Pass | 2025-06-19 | Done
DS-15 | DS_issues | Dynamic Address Validation Test | SVB | I3C | Pass | 2025-05-31 | Done
DS-16 | DS_issues | Multimaster Address Assign test | SVB | I3C | Pass | 2025-06-07 | Done
DS-18 | DS_issues | Bit Timing Test | JTAMP | CAN | Fail | 2025-06-12 | Done
DS-32 | DS_issues | Auto-negotiation Test | SVB | Ethernet | Pass | 2025-06-07 | Done
DS-40 | DS_issues | Instruction Register Validation | SVB | JTAG | In Progress | 2025-06-23 | Unresolved
DS-19 | DS_issues | Bus Load Measurement | JTAEN | CAN | Fail | 2025-06-18 | Done
DS-26 | DS_issues | Error correction code check | JTAMP | PCIe | Fail | 2025-05-29 | Done
DS-27 | DS_issues | Throughput measurement | JTAEN | PCIe | Pass | 2025-06-06 | Done
DS-30 | DS_issues | Latency Measurement | JTAES | Ethernet | Pass | 2025-06-14 | Done
DS-31 | DS_issues | Collision Measurement | SVB | Ethernet | Pass | 2025-06-03 | Done

## Pass
Issue Key | Filter | Summary | Platform | IP | Status | Due Date | Resolution
DS-34 | Ovr_Pass_Filter | Frame error Analysis | JTAMP | LIN | Pass | 2025-06-07 | Done
DS-32 | Ovr_Pass_Filter | Auto-negotiation Test | SVB | Ethernet | Pass | 2025-06-07 | Done
DS-31 | Ovr_Pass_Filter | Collision Measurement | SVB | Ethernet | Pass | 2025-06-03 | Done
DS-30 | Ovr_Pass_Filter | Latency Measurement | JTAES | Ethernet | Pass | 2025-06-14 | Done
DS-29 | Ovr_Pass_Filter | Packet Intergrity Analysis | JTAES | Ethernet | Pass | 2025-06-06 | Done
DS-27 | Ovr_Pass_Filter | Throughput measurement | JTAEN | PCIe | Pass | 2025-06-06 | Done
DS-24 | Ovr_Pass_Filter | Hot Plug Detection | SVB | USB | Pass | 2025-06-06 | Done
DS-22 | Ovr_Pass_Filter | Data Transfer Test Communication | JTAES | USB | Pass | 2025-06-07 | Done
DS-21 | Ovr_Pass_Filter | End point communication | JTAES | USB | Pass | 2025-06-06 | Done
DS-20 | Ovr_Pass_Filter | Node communication Verification | JTAEN | CAN | Pass | 2025-05-31 | Done
DS-17 | Ovr_Pass_Filter | Error Frame Analysis | JTAMP | CAN | Pass | 2025-06-06 | Done
DS-16 | Ovr_Pass_Filter | Multimaster Address Assign test | SVB | I3C | Pass | 2025-06-07 | Done
DS-15 | Ovr_Pass_Filter | Dynamic Address Validation Test | SVB | I3C | Pass | 2025-05-31 | Done
DS-14 | Ovr_Pass_Filter | Bus Arbitration Test | JTAES | I3C | Pass | 2025-06-07 | Done
DS-11 | Ovr_Pass_Filter | Pull-up register Validation | JTAEN | I2C | Pass | 2025-06-25 | Done
DS-10 | Ovr_Pass_Filter | Bus Speed Analysis | JTAMP | I2C | Pass | 2025-06-19 | Done
DS-9 | Ovr_Pass_Filter | Address Conflict detection | JTAMP | I2C | Pass | 2025-06-01 | Done
DS-5 | Ovr_Pass_Filter | Clock synchronisation Test | JTAES | SPI | Pass | 2025-06-23 | Done
DS-2 | Ovr_Pass_Filter | Parity Check Test | JTAMP | UART | Pass | 2025-06-06 | Done

## Fail
Issue Key | Filter | Summary | Platform | IP | Status | Due Date | Resolution
DS-39 | Ovr_Fail_Filter | Signal Timing Analysis | JTAES | JTAG | Fail | 2025-06-21 | Done
DS-38 | Ovr_Fail_Filter | Debug Interface Check | JTAES | JTAG | Fail | 2025-06-12 | Done
DS-37 | Ovr_Fail_Filter | Boundary Scan Test | JTAES | Ethernet | Fail | 2025-06-05 | Done
DS-36 | Ovr_Fail_Filter | Slave Response Time check | JTAEN | LIN | Fail | 2025-05-30 | Done
DS-26 | Ovr_Fail_Filter | Error correction code check | JTAMP | PCIe | Fail | 2025-05-29 | Done
DS-19 | Ovr_Fail_Filter | Bus Load Measurement | JTAEN | CAN | Fail | 2025-06-18 | Done
DS-18 | Ovr_Fail_Filter | Bit Timing Test | JTAMP | CAN | Fail | 2025-06-12 | Done
DS-13 | Ovr_Fail_Filter | Address Conflict detection | JTAES | I3C | Fail | 2025-05-31 | Done
DS-12 | Ovr_Fail_Filter | Clock Streching Test | JTAEN | I2C | Fail | 2025-05-30 | Done
DS-7 | Ovr_Fail_Filter | Salve select Validation | SVB | SPI | Fail | 2025-06-05 | Done
DS-4 | Ovr_Fail_Filter | Loopback Test | JTAEN | UART | Fail | 2025-07-18 | Done
DS-3 | Ovr_Fail_Filter | Signal Integrity Test | JTAEN | UART | Fail | 2025-06-04 | Done
DS-1 | Ovr_Fail_Filter | Baud Rate Test | JTAMP | UART | Fail | 2025-06-20 | Done

## Unresolved
Issue Key | Filter | Summary | Platform | IP | Status | Due Date | Resolution
DS-35 | Ovr_ToDo_Filter | Bus Voltage Measurement | JTAEN | LIN | To Do | 2025-06-06 | Unresolved
DS-33 | Ovr_ToDo_Filter | Signal Synchronization Test | JTAMP | LIN | To Do | 2025-06-07 | Unresolved
DS-25 | Ovr_ToDo_Filter | Lane speed Test | JTAMP | PCIe | To Do | 2025-06-04 | Unresolved
DS-23 | Ovr_ToDo_Filter | Power consumption Analysis | SVB | USB | To Do | 2025-05-31 | Unresolved
DS-6 | Ovr_ToDo_Filter | Data Transfer Test | JTAES | SPI | To Do | 2025-06-19 | Unresolved